## User Journey
TC ID | Test Case | Test Data / Steps | Expected Result | Status | Actual Result / Evidence
U0 | Precondition - DB connectivity | Site + backend + database must be up (health check). | GET /api/health returns 200 ok:true | FAIL | GET /api/health -> 500. Body: cluster reached monthly Request Unit limit and is now DISABLED by Aiven.
U1.1 | Home page loads | Open https://project1-15uq.onrender.com | Page loads, hero + featured sections shown | BLOCKED | GET / -> 500 (Next.js __next_error__, DB down). Renders title only.
U1.2 | Featured products on home | Browse home for featured items | Featured products visible | NOT RUN | Cannot load (DB down).
U1.3 | Header navigation visible | Check Home/Menu/Cart/Login/Register links | Links visible and clickable | PASS | Header rendered on pages that load (200).
U1.4 | Footer visible | Scroll to footer (About/Contact/T&C/Privacy) | Footer links render | NOT RUN | Not verifiable while home is 500.
U1.5 | SEO title/meta | Inspect <title> and meta tags | Proper title + description | PASS | Title 'Neon Bites - Fresh Local Food.' present.
U2.1 | Menu page lists all products | Open /menu | Products grid shown | BLOCKED | GET /menu -> 500 (DB down).
U2.2 | Category filter | Select a category on /menu | Only that category's items shown | NOT RUN | DB down.
U2.3 | Veg filter | Toggle veg/non-veg | Filter applied | NOT RUN | DB down.
U2.4 | Availability filter | Toggle availability | Filter applied | NOT RUN | DB down.
U2.5 | Search by name | Type product name in search box | Matching products shown | NOT RUN | DB down.
U2.6 | Sort on menu | Sort by price/top/name | Order changes correctly | NOT RUN | DB down.
U2.7 | Pagination | Navigate pages on /menu | Page 2 loads | NOT RUN | DB down.
U2.8 | Empty results state | Search a term with no match | Friendly 'no results' message | NOT RUN | DB down.
U3.1 | Product detail loads | Open a product page | Image/price/desc/stock shown | NOT RUN | DB down (no product data).
U3.2 | Add to cart (logged in) | Logged in -> product -> Add to cart | Item added, toast + cart count updates | NOT RUN | DB down.
U3.3 | Add to cart (guest) | Not logged in -> Add to cart | Redirect to /auth/login?next=/cart | PASS | Middleware redirect logic confirmed; cart page renders 200. Full flow blocked (DB).
U3.4 | Add out-of-stock item | Try adding an out-of-stock product | Error message, not added | NOT RUN | DB down.
U3.5 | Quantity respects stock | Set qty above stock | Value capped at stock limit | NOT RUN | DB down.
U3.6 | Related products | View product detail | Related items shown | NOT RUN | DB down.
U4.1 | Register new account | Register with unique email + valid data | 200, account created, logged in | NOT RUN | DB down (register hits DB).
U4.2 | Register duplicate email | Register with existing email | Friendly error | NOT RUN | DB down.
U4.3 | Register validation | Invalid email / short or missing password / mismatched confirm | Inline validation errors | NOT RUN | DB down.
U4.4 | Login valid customer | POST /api/auth/login srikantak@yahoo.com / [REDACTED] | 200, session cookie set, redirect | FAIL | POST -> 500 {'error':'Something went wrong. Please try again.'} due to DB disabled. Credentials are correct in seed.
U4.5 | Login invalid password | Valid email + wrong password | 401 'Invalid email or password.' | NOT RUN | DB down - cannot distinguish/complete.
U4.6 | Login unknown email | Non-existent email + any password | 401 error | NOT RUN | DB down.
U4.7 | Login rate limiting | Attempt login repeatedly | 429 after threshold (rate-limited) | NOT RUN | DB down - 500 returned before rate logic could be validated.
U4.8 | Forgot password flow | Request reset for existing email | Reset email sent (EmailLog) | NOT RUN | DB + SMTP dependent.
U4.9 | Reset password valid token | Use valid token to set new password | Password updated, login works | NOT RUN | DB down.
U4.10 | Reset invalid/expired token | Use bad token | Clear error | NOT RUN | DB down.
U4.11 | Deactivated customer login | Try login with isActive=false account | Blocked with message | NOT RUN | DB down.
U4.12 | Logout | Click Logout | Session cleared, redirect home | NOT RUN | Requires logged-in session.
U5.1 | Cart page loads | Open /cart | Cart page renders | PASS | GET /cart -> 200 (client UI). Items require DB.
U5.2 | Update quantity | Change quantity in cart | Total recalcs, persisted | NOT RUN | DB down.
U5.3 | Remove item | Remove item from cart | Item removed, total updates | NOT RUN | DB down.
U5.4 | Cart total recalculated | Add/remove items | Server-side total correct | NOT RUN | DB down.
U5.5 | Empty cart state | Open cart with no items | 'Your cart is empty' prompt | NOT RUN | DB down.
U5.6 | Guest cart prompt | Guest opens cart | Prompt to login | NOT RUN | DB down.
U5.7 | Cart persists across sessions | Save a cart, revisit later | Same DB-backed cart | NOT RUN | DB down.
U6.1 | Checkout page loads | Logged-in user opens /checkout | Cart lines + address section shown | BLOCKED | Guest /checkout -> 307 (PASS); with session needs DB -> unreachable while DB down.
U6.2 | Checkout requires login | Guest opens /checkout | Redirect to /auth/login?next=/checkout | PASS | GET /checkout (no cookie) -> 307 to /auth/login?next=/checkout.
U6.3 | Select saved address | Choose an existing address | Address selected on order | NOT RUN | DB down.
U6.4 | Add new address at checkout | Add new address | Address saved, selectable | NOT RUN | DB down.
U6.5 | Set default address | Mark address as default | Persisted as default | NOT RUN | DB down.
U6.6 | PIN serviceability check | Enter serviceable / non-serviceable PIN | Serviceable accepted; others warned | NOT RUN | DB down.
U6.7 | Customer notes | Add a note at checkout | Note saved with order | NOT RUN | DB down.
U6.8 | Server-side price recalc | Place order | Totals recomputed server-side | NOT RUN | DB down.
U6.9 | Place order without address | Submit with no address | Validation error | NOT RUN | DB down.
U7.1 | Payment page loads | After order, open payment page | Payment page with order + total | NOT RUN | DB + payment provider required.
U7.2 | UPI QR generation | Request QR for own order | QR returned; ownership enforced | NOT RUN | DB down.
U7.3 | Payment success verified server-side | Simulate success UPI payment | HMAC verified, order confirmed | NOT RUN | Requires Razorpay/mock - mock blocked in prod.
U7.4 | Payment failure | Simulate failed payment | Order failed, retry allowed | NOT RUN | Requires payment provider.
U7.5 | Abandoned payment | Leave payment incomplete | Order stays PENDING_PAYMENT | NOT RUN | Requires payment provider.
U7.6 | Duplicate webhook idempotency | Send same webhook twice | No double confirm/stock/email | NOT RUN | Requires payment provider.
U8.1 | Order success page | After confirmed payment | Order number + total shown | NOT RUN | DB down.
U8.2 | Confirmation email | Check EmailLog after order | HTML confirmation email logged | NOT RUN | Requires SMTP + DB.
U8.3 | Order in My Orders | Open /account/orders | New order listed | NOT RUN | DB down.
U9.1 | Account overview | Open /account | Welcome + recent orders | BLOCKED | Guest /account -> 307 (PASS); data requires DB.
U9.2 | Update profile | Edit name/phone | Persisted, toast confirms | NOT RUN | DB down.
U9.3 | Address book CRUD | Add/edit/delete/set default | All changes persist | NOT RUN | DB down.
U9.4 | Change password | Provide old + new + confirm | Requires current password; updates | NOT RUN | DB down.
U9.5 | My Orders list & filters | Open /account/orders, filter by status | Correct filtered list | NOT RUN | DB down.
U9.6 | Order detail + timeline | Open an order | Full status timeline shown | NOT RUN | DB down.
U9.7 | Access another user's order | Open someone else's order number | 404 (ownership enforced) | NOT RUN | DB down.
U10.1 | Live order status tracking | Customer views order after status changes | Shows current stage | NOT RUN | DB down.
U10.2 | Timeline advances | Admin advances status | Customer sees new stage | NOT RUN | DB down.

## Admin Journey
TC ID | Test Case | Test Data / Steps | Expected Result | Status | Actual Result / Evidence
A1.1 | Admin API blocked for anonymous | GET /api/admin/products (no cookie) | 401 Unauthorized | PASS | GET /api/admin/products (anon) -> 401.
A1.2 | Customer blocked from admin API | Login as customer, call admin API | 403 Forbidden | NOT RUN | Needs DB login; cannot obtain customer session while DB down.
A1.3 | Admin login | POST /api/auth/login srikantak1@gmail.com / [REDACTED] | 200 + session cookie | FAIL | POST -> 500 due to DB disabled. Admin creds are correct in seed (bootstrap.ts).
A1.4 | Admin area requires login | GET /admin (no cookie) | 307 redirect to /auth/login?next=/admin | PASS | GET /admin (anon) -> 307 to /auth/login?next=%2Fadmin.
A1.5 | Nested admin pages redirect | GET /admin/products, /admin/orders (anon) | 307 to login with next | PASS | Both -> 307 to /auth/login with next set.
A2.1 | Dashboard renders KPIs | Open /admin as admin | Revenue/orders/customers KPIs | BLOCKED | Requires login + DB; not reachable.
A2.2 | Charts render | View dashboard | Recharts render without JS errors | NOT RUN | DB down.
A2.3 | Recent orders on dashboard | View dashboard | Recent orders listed | NOT RUN | DB down.
A2.4 | Star threshold / target display | View dashboard | Target shown correctly | NOT RUN | DB down.
A3.1 | List categories | GET /api/admin/categories | 200 list | NOT RUN | DB down.
A3.2 | Create category | POST name/description/displayOrder/isActive | 201 created | NOT RUN | DB down.
A3.3 | Duplicate category name | Create category with existing slug | Unique slug, no crash (201) | NOT RUN | DB down.
A3.4 | Update category | PATCH category | 200 updated | NOT RUN | DB down.
A3.5 | Archive/delete category | DELETE category | Soft-deleted, hidden from store | NOT RUN | DB down.
A3.6 | Category validation | Create with empty name | Zod validation error | NOT RUN | DB down.
A4.1 | List products | GET /api/admin/products | 200 list with filters/pagination | NOT RUN | DB down.
A4.2 | Create product | POST full product data | 201 created | NOT RUN | DB down.
A4.3 | Update product | PATCH product | 200 updated | NOT RUN | DB down.
A4.4 | Soft-archive product | DELETE product | Removed from storefront | NOT RUN | DB down.
A4.5 | Toggle availability/featured | PATCH toggle endpoint | 200 toggled | NOT RUN | DB down.
A4.6 | Duplicate SKU | Create/update with duplicate SKU | Friendly error | NOT RUN | DB down.
A4.7 | Product validation | Price<=0 / missing category / negative stock | Zod error | NOT RUN | DB down.
A4.8 | Inventory decremented on order | Complete a paid order | Stock reduced by qty | NOT RUN | DB down.
A5.1 | List orders | GET /admin/orders + status filter/search | 200 filtered list | NOT RUN | DB down.
A5.2 | Order detail | Open an order | Items/customer/payment/address shown | NOT RUN | DB down.
A5.3 | Valid status transitions | CONFIRMED -> PREPARING -> READY -> OUT_FOR_DELIVERY -> DELIVERED | Each returns 200, order advances | NOT RUN | DB down.
A5.4 | Invalid status transition | Attempt PENDING_PAYMENT -> DELIVERED directly | 409 rejected | NOT RUN | DB down.
A5.5 | Payment verification updates status | Verify UPI credit | Order confirmed after verified payment | NOT RUN | DB + payment provider.
A5.6 | Non-existent order | Patch status of FOOD-99999999-000001 | 404 handled | NOT RUN | DB down.
A5.7 | Audit log on status change | Advance an order status | AdminAuditLog entry created | NOT RUN | DB down.
A6.1 | Payments list renders | Open /admin/payments | 200; gateway secrets hidden | NOT RUN | DB down.
A6.2 | Confirm captured payment | Mark payment captured | Payment confirmed, order updated | NOT RUN | DB + payment provider.
A6.3 | Failed payment handling | Mark payment failed | Order failed, notify customer | NOT RUN | DB + payment provider.
A7.1 | List customers | GET /admin/customers | 200 list | NOT RUN | DB down.
A7.2 | Customer detail/orders | Open a customer | Profile + order history | NOT RUN | DB down.
A7.3 | Deactivate customer | PATCH customer isActive=false | 200; customer blocked | NOT RUN | DB down.
A7.4 | Reactivate customer | PATCH customer isActive=true | 200; customer can log in | NOT RUN | DB down.
A7.5 | Unknown customer id | PATCH nonexistent-id | 404 handled | NOT RUN | DB down.
A8.1 | Reports page renders KPIs | Open /admin/reports | 200 with Revenue metrics | NOT RUN | DB down.
A8.2 | Daily sales report | Load daily-sales report | Correct totals | NOT RUN | DB down.
A8.3 | Product performance report | Load product report | Correct ranking | NOT RUN | DB down.
A8.4 | Category report | Load category report | Correct aggregation | NOT RUN | DB down.
A8.5 | Custom report builder | GET /admin/reports/custom?preset&dimension&metrics | 200 builder renders | NOT RUN | DB down.
A8.6 | CSV export | GET /api/admin/reports/export?type=daily-sales | 200 text/csv with metadata | NOT RUN | DB down.
A8.7 | CSV export blocked for anonymous | GET export URL without cookie | 401/307 | NOT RUN | DB down.
A9.1 | Settings page renders | Open /admin/settings | 200 with settings | NOT RUN | DB down.
A9.2 | DB credentials hidden | Inspect settings HTML | No 'postgresql://' / secrets leaked | NOT RUN | DB down.
A9.3 | Update settings | Edit settings, save | Persisted | NOT RUN | DB down.
A10.1 | Audit log lists actions | Open /admin/audit-logs | 200 list | NOT RUN | DB down.
A10.2 | Sensitive actions logged | Create product / change status | Audit entry with who/what/when | NOT RUN | DB down.
A10.3 | Filter audit by actor/action | Apply filters | Filtered results | NOT RUN | DB down.

## Bugs & Findings
Bug ID | Severity | Module | Description | Steps to Reproduce | Expected | Actual | Status
BUG-1 | Critical | Database / Aiven | Aiven PostgreSQL cluster hit its monthly Request Unit (computing unit) limit and is DISABLED. Every DB query fails -> all DB-backed features return 500, including login. | Open site or hit /api/auth/login / /api/health | All DB-backed features work (200) | GET /api/health -> 500 ok:false; login -> 500; home/menu -> 500 | BLOCKED
BUG-1a | Critical | Login (Customer) | Login for srikantak@yahoo.com / [REDACTED] fails because of BUG-1, NOT because of wrong credentials. | POST /api/auth/login srikantak@yahoo.com / [REDACTED] | 200 + session cookie | 500 {'error':'Something went wrong. Please try again.'} | BLOCKED
BUG-1b | Critical | Login (Admin) | Admin login srikantak1@gmail.com / [REDACTED] fails for the same DB reason. | POST /api/auth/login srikantak1@gmail.com / [REDACTED] | 200 + session cookie | 500 due to disabled DB | BLOCKED
BUG-2 | Medium | SEO / Config | robots.txt Sitemap URL points to http://localhost:3000/sitemap.xml instead of the deployed domain. | GET /robots.txt | Sitemap: https://project1-15uq.onrender.com/sitemap.xml | Sitemap: http://localhost:3000/sitemap.xml | BUG
INFO-1 | Info | Payment | PAYMENT_MODE=direct is set in Render blueprint (mock blocked in prod). Full E2E payment needs Razorpay keys + webhook configured. | Complete checkout/payment | Payment goes through Razorpay | Mock blocked in prod - cannot complete UPI payment without Razorpay setup | NOT RUN
INFO-2 | Info | DB Seeding | Seed defines customer srikantak@yahoo.com and admin srikantak1@gmail.com, both password [REDACTED] (prisma/bootstrap.ts). Users exist if DB was seeded before it got disabled. | npm run prisma:bootstrap | Both users created | Cannot verify while DB disabled | NOT RUN

## Summary
Metric | Value
Application under test | Neon Bites - project1-15uq.onrender.com
Test Date | 2026-10-02
User Journey test cases | 66
Admin Journey test cases | 51
Total test cases | 117
PASS (verified live) | 8 - U1.3, U1.5, U3.3, U5.1, U6.2, A1.1, A1.4, A1.5
FAIL (blocked by disabled DB) | 3 - U0 (health), U4.4 (customer login), A1.3 (admin login)
BLOCKED (cannot execute - DB down) | 5 - U1.1, U2.1, U6.1, U9.1, A2.1
NOT RUN (DB / payment / email dependent) | 101 - the remaining cases
Bugs found | 2 - BUG-1 Critical (Aiven DB outage), BUG-2 Medium (localhost sitemap)
Top blocker / Recommended action | Fix BUG-1: In Aiven console increase / refill the monthly Request Unit limit to re-enable the cluster, then re-run 'npm run prisma:bootstrap'. Then re-run all BLOCKED / NOT RUN cases.
Why login fails | The login failure is NOT a credentials problem - the Aiven database is disabled (monthly Request Unit limit exceeded). Every DB query returns 500.
Reference credentials (from seed) | Customer: srikantak@yahoo.com / [REDACTED] ¦ Admin: srikantak1@gmail.com / [REDACTED]